## updated_ai_engineering_pipeline
Stage | Name of Stage | Precursor Stage(s) | Author | Reviewer | Deliverable 1 | Deliverable 2 | Deliverable 3 | Deliverable 4 | Deliverable 5 | Legend
1 | Product Requirements Document (PRD) | N/A | Manual Input | DeepSeek-R1:7b for content review and Gemma3:4b for structuring | Product Name, Product Description, List of functions/systems comprising the product ,Hardware platform/Cloud platform/Software platform it will be based on for webapp, Android app, BFF and Backend plus Github link to save online in addtion to local | Generic description of each function and scope of each function wrt to infrastructure like webapp, android app, BFF and Backend. | External product/system linkages | Context Diagram (C4 Methodology) | Open questions, assumptions, ambiguities |  | Author to Produce Initial version. Following review, AI can update this.
2 | System Requirements Specification (SRS/FRS) | 1 | Manual input for Deliverable 1. LLM generation for Deliverables 2-5 | Qwen2.5-Coder:7B for Manual Review + Gemma3:4b for structuring. | Detailed requirements split into Frontend, Android App, BFF and Backend | High-level state machines | Flowcharts of functions. This will show cross-functional impact. | Container Diagram (C4 Methodology) | System invariants document |  | Author to Review as per checklist
3 | Requirements Validation Gate | 2 | Manual Review for deliverables 1-4. Deliverable 5 by LLM Qwen2.5-Coder:7B | DeepSeek-R1:7b | Contradiction review | Ambiguity review | Missing requirements review | Concurrency and offline-risk review | Approved finalized requirements (PRS/SRS/FRS) |  | AI Generated
4 | Software Requirements Document (Architecture + Contracts) | 3 | Qwen2.5-Coder:7B | Manual Review | Data schema of functions | UML diagrams of functions | OpenAPI YAML files | PlantUML stencil screens for Frontend/Android | Component Diagram (C4 Methodology)
5 | Security and Architecture Validation Gate | 4 | DeepSeek-R1:7B | Manual Review | Security review | Offline sync/race-condition review | Architecture consistency review | Dependency validation review | Architecture freeze approval
6 | Software Design Document + Atomic Task Generation | 5 | Qwen2.5-Coder:7B or Qwen3.5:4B | Manual Review | Detailed atomic task list mapped 1:1 to implementation | Deployment/configuration manual | Folder structure and repository layout | Development and curl-based verification document | Dependency graph JSON + context packets
7 | Task Validation Gate | 6 | Manual Review | Qwen3.5:4B | Oversized task detection | Hidden dependency review | Task ambiguity review | Context-window suitability review | Approved task graph
8 | Local Task-by-Task Code Generation | 7 | Qwen2.5-Coder:7B / Llama3:8B | Manual Review + DeepSeek-R1:7B | Generated code | Unit tests | Proposed DTO/API change requests | Implementation notes | Code review findings
9 | Integration and Deployment Validation | 8 | Phi3:mini / Qwen3.5:4B for deliverable 1. Manual update for rest. | Manual Review | Integration validation report | Contract mismatch review | Regression verification checklist | Deployment readiness review | Release approval

## Traceability_sheet
Stage | Output | Deliverables | Description | Reason for Requesting | Manually Typed in Initially | LLM Review | Reason for LLM Review | Tag (Stage_Output_Deliverables_ManualorAI_entering_time) | Tag Legend for AorM |  | Tool Requirements | Tag Requirements
S1 | PRD | D1.1 | Product name | This requirement capture app (RCA) will mention that name is required to create a new folder with Product Name at the default location. Default location is configurable in pipeline settings tab, if not will default to C:/RCA/<Product_Name> | Y | Y | Check if name is not a funny name and makes sense? If not making sense, confirm with user if not give output that seems ok | S1_PRD_D1.1_(AorM)_(time) | Manually_Generated_firstpass | MGFP | Questions and Statements made from Column Deliverables.
S1 | PRD | D1.2 | Product Description | This requirement capture app (RCA) will only state that lets proceed with product description. | N | N | Statement only. Cross compare this section for impact on ambiguities, open questions and assumptions. | S1_PRD_D1.2_(AorM)_(time) | AI_Generated_firstpass | AGFP | Hint for Answers is given in column "Reason for Requesting"
S1 | PRD | D1.2.1 | Business Purpose of Product | RCA will require user to manually enter the business purpose of the product. | Y | Y | D5 | S1_PRD_D1.2.1_(AorM)_(time) | AI_Generated_Review_Manualentry | AGRM | Based on Column "Manually typed in Initially", some answers are typed in manually from the questions. | Select tag MGFP if this is first time manually generated.
S1 | PRD | D1.2.2 | Explain for a new user what will happen on first click? | RCA will require user to describe workflow for new user who has never used the product. | Y | Y | D5 | S1_PRD_D1.2.2_(AorM)_(time) | Manually_Accepted_AI_Proposal | MAAP | Answers are subject to different types of LLM reviews.
S1 | PRD | D1.2.3 | Describe the types of users | This requirement capture app (RCA) will only state that lets proceed with describing the types of users. | N | N | Statement only | S1_PRD_D1.2.3_(AorM)_(time) | Manually_Edited_AI_Proposal | MEAP | Stage LLM review will be carried out in sequence after all manual fields filled in.
S1 | PRD | D1.2.3.1 | Will you have a normal user who only looks at reading data from your product? | Read-only normal user check | Y | Y | D5 | S1_PRD_D1.2.3.1_(AorM)_(time) | Manually_Rejected_AI_Proposal | MRAP | LLM Review will highlight ambiguities, open questions and assumptions for every task marked as needing "LLM Review" in column.
S1 | PRD | D1.2.3.2 | Will you have a normal user who only looks at writing data to your product? | Write normal user check | Y | Y | D5 | S1_PRD_D1.2.3.2_(AorM)_(time) |  |  | This LLM Review will be done one by one for each in "Tag" column by LLM selected (Either local LLM via Ollama or Cloud LLM via key) | LLM review will be marked AGRM as per tag legend when it has been created. If reviewed but no comments, it should still be marked AGRM since review was done. Tags to be done as per "Tag" colum. If review skipped, then don’t tag at all.
S1 | PRD | D1.2.3.3 | Will you have a paid/premium user who looks at writing data to your product and seeking paid/premium features to access? | Write paid/premium user check | Y | Y | D5 | S1_PRD_D1.2.3.3_(AorM)_(time) |  |  | If reference to section number is made in "Reason for LLM Review" e.g. D5, then skip review for that tag. The review will be conducted in section noted.
S1 | PRD | D1.2.3.4 | How many different sub-types of paid/premium users will you need? | Will the paid user segment be divided as well with some a paid-lite users and other premium-heavy users? Or do we have more categories? | Y | Y | D5 | S1_PRD_D1.2.3.4_(AorM)_(time) |  |  | The entire history of Manual additions and AI reviews will be captured via tags in a json file. This will allow all choices to be replayed. Note that the "Tag" column includes a time field. So when manually entered, time of entry will be added here. If AI review is done, the time of AI review completion willl be here. If AI review accepted manually, that time of acceptance will be in this field. Same for edited or rejected.
S1 | PRD | D1.2.3.5 | Do you need an admin page for colleagues working on your product? | Check if product needs admin login. | Y | Y | D5 | S1_PRD_D1.2.3.5_(AorM)_(time) |  |  | Max_functions_per_product = 10
S1 | PRD | D1.2.3.6 | Do you need a super-admin page for your product? | Check if product needs super-admin login | Y | Y | D5 | S1_PRD_D1.2.3.6_(AorM)_(time) |  |  | The json file shall be automatically saved when clicking D5 autochecks.
S1 | PRD | D1.3 | Do you need files to be stored on Github or only locally? A github repo with same name as in D1.1 will be started. | Check if Github is needed? | Y | N | Setting up Github folder only | S1_PRD_D1.3_(AorM)_(time) |  |  | There shall be a button to periodically save the json file.
S1 | PRD | D1.4 | Lets proceed with a list of functions for your product. | To split the product in specific functions. | N | N | Statement only | S1_PRD_D1.4_(AorM)_(time)
S1 | PRD | D1.4.1 | How many functions? Enter Integer. Imagine we are cutting the product horizontally. How many different slices can be made? | To get the list of functions that comprise the product. | Y | Y | D5 | S1_PRD_D1.4.1_(AorM)_(time)
S1 | PRD | D1.4.2.1 | Name of function 1 | Get a list of names of all the functions | Y | Y | Check if the names are proper and make sense and are not random. | S1_PRD_D1.4.2.1_(AorM)_(time)
S1 | PRD | D1.4.2.x | Name of function x | Get a list of names of all the functions | Y | Y | D5 | S1_PRD_D1.4.2.x_(AorM)_(time)
S1 | PRD | D2 | Lets summarize each function noted | This requirement capture app (RCA) will only state that lets proceed with describing the functions. | N | N | Statement only | S1_PRD_D2_(AorM)_(time)
S1 | PRD | D2.1.1 | Function 1 summary | Summary of function 1 | Y | Y | D5 | S1_PRD_D2.1.1_(AorM)_(time)
S1 | PRD | D2.1.x | Function x summary | Summary of function x | Y | Y | D5 | S1_PRD_D2.1.x_(AorM)_(time)
S1 | PRD | D1.6 | What type of infrastructure will your product need? Split the infrastructure as per use cases. | To split the product in specific infrastructure | N | N | Statement only | S1_PRD_D1.6_(AorM)_(time)
S1 | PRD | D1.6.1.1 | Webapp for normal read-only and paid/premium users? | If public facing webapp is required? | Y | Y | D5 | S1_PRD_D1.6.1.1_(AorM)_(time)
S1 | PRD | D1.6.1.2 | Where will it be hosted? | CF Pages | Y | Y | D5 | S1_PRD_D1.6.1.2_(AorM)_(time)
S1 | PRD | D1.6.1.3 | What language is expected to be used? | Hono TS | Y | Y | D5 | S1_PRD_D1.6.1.3_(AorM)_(time)
S1 | PRD | D1.6.2.1 | Webapp for admin users and super-admins? | If private webapp is required? | Y | Y | D5 | S1_PRD_D1.6.2.1_(AorM)_(time)
S1 | PRD | D1.6.2.2 | Where will it be hosted? | CF Pages | Y | Y | D5 | S1_PRD_D1.6.2.2_(AorM)_(time)
S1 | PRD | D1.6.2.3 | What language is expected to be used? | Hono TS | Y | Y | D5 | S1_PRD_D1.6.2.3_(AorM)_(time)
S1 | PRD | D1.6.3.1 | Android app for normal and paid/premium users? | If public facing android app is required? | Y | Y | D5 | S1_PRD_D1.6.3.1_(AorM)_(time)
S1 | PRD | D1.6.3.2 | Where will it be built? Local/ Github actions? | To check if github.yml is required. | Y | Y | D5 | S1_PRD_D1.6.3.2_(AorM)_(time)
S1 | PRD | D1.6.3.3 | What language is expected to be used? | Kotlin/KMM | Y | Y | D5 | S1_PRD_D1.6.3.3_(AorM)_(time)
S1 | PRD | D1.6.4.1 | Android app for normal and paid/premium users? | If private android app is required? | Y | Y | D5 | S1_PRD_D1.6.4.1_(AorM)_(time)
S1 | PRD | D1.6.4.2 | Where will it be built? Local/ Github actions? | To check if github.yml is required. | Y | Y | D5 | S1_PRD_D1.6.4.2_(AorM)_(time)
S1 | PRD | D1.6.4.3 | What language is expected to be used? | Kotlin/KMM | Y | Y | D5 | S1_PRD_D1.6.4.3_(AorM)_(time)
S1 | PRD | D1.6.5.1 | BFF with public URL for normal and paid/premium users? | If public facing URL with BFF is required? | Y | Y | D5 | S1_PRD_D1.6.5.1_(AorM)_(time)
S1 | PRD | D1.6.5.2 | Where will it be hosted? | CF Worker | Y | Y | D5 | S1_PRD_D1.6.5.2_(AorM)_(time)
S1 | PRD | D1.6.5.3 | What language is expected to be used? | Hono TS | Y | Y | D5 | S1_PRD_D1.6.5.3_(AorM)_(time)
S1 | PRD | D1.6.6.1 | BFF with private URL? | If private URL is required? For login, external endpoints and admins/super-admins, private URLs can be required. | Y | Y | D5 | S1_PRD_D1.6.6.1_(AorM)_(time)
S1 | PRD | D1.6.6.2 | Where will it be hosted? | CF Worker | Y | Y | D5 | S1_PRD_D1.6.6.2_(AorM)_(time)
S1 | PRD | D1.6.6.3 | What language is expected to be used? | Hono TS | Y | Y | D5 | S1_PRD_D1.6.6.3_(AorM)_(time)
S1 | PRD | D1.6.7.1 | Permanent Database backend ? | Required? | Y | Y | D5 | S1_PRD_D1.6.7.1_(AorM)_(time)
S1 | PRD | D1.6.7.2 | Where will it be hosted? | Supabase Cloud | Y | Y | D5 | S1_PRD_D1.6.7.2_(AorM)_(time)
S1 | PRD | D1.6.7.3 | What database? | Postgres | Y | Y | D5 | S1_PRD_D1.6.7.3_(AorM)_(time)
S1 | PRD | D1.6.8.1 | Permanent Database functions? | Required? | Y | Y | D5 | S1_PRD_D1.6.8.1_(AorM)_(time)
S1 | PRD | D1.6.8.2 | Where will it be hosted? | Supabase Cloud Edge Functions | Y | Y | D5 | S1_PRD_D1.6.8.2_(AorM)_(time)
S1 | PRD | D1.6.8.3 | What language is expected to be used? | Hono TS | Y | Y | D5 | S1_PRD_D1.6.8.3_(AorM)_(time)
S1 | PRD | D1.6.9.1 | In-store memory database? | Required? | Y | Y | D5 | S1_PRD_D1.6.9.1_(AorM)_(time)
S1 | PRD | D1.6.9.2 | Where will it be hosted? | Hetzner Coolify | Y | Y | D5 | S1_PRD_D1.6.9.2_(AorM)_(time)
S1 | PRD | D1.6.9.3 | What database? | Dragonfly/ Redis | Y | Y | D5 | S1_PRD_D1.6.9.3_(AorM)_(time)
S1 | PRD | D1.6.10.1 | In-store memory database functions? | Required? | Y | Y | D5 | S1_PRD_D1.6.10.1_(AorM)_(time)
S1 | PRD | D1.6.10.2 | Where will it be hosted? | Hetzner Coolify | Y | Y | D5 | S1_PRD_D1.6.10.2_(AorM)_(time)
S1 | PRD | D1.6.10.3 | What language is expected to be used? | Python/Cpp/Rust/Go | Y | Y | D5 | S1_PRD_D1.6.10.3_(AorM)_(time)
S1 | PRD | D3 | Lets start with External linkages for externla products | This requirement capture app (RCA) will only state that lets proceed with capturing details of the external linkages | N | N | Statement only | S1_PRD_D3_(AorM)_(time)
S1 | PRD | D3.1 | Will the external products interface with the product? E.g. External SMS reciever or External SMS sender or Payment gateway like Razorpay. | To check if external products will interface? | Y | Y | D5 | S1_PRD_D3.1_(AorM)_(time)
S1 | PRD | D3.2 | Will it interface with BFF or Permanent Database Backend function or In-memory database backend function? Check the boxes. | To check how the external products interface. | Y | Y | D5 | S1_PRD_D3.2_(AorM)_(time)
S1 | PRD | D3.3.1 | Which external function intefaces with BFF? | Initial external function that interfaces with BFF | Y | Y | D5 | S1_PRD_D3.3.1_(AorM)_(time)
S1 | PRD | D3.3.j | Which external product intefaces with BFF? Keep on asking, is there another external product that interfaces with BFF? | Jth external function that interfaces with BFF | Y | Y | D5 | S1_PRD_D3.3.j_(AorM)_(time)
S1 | PRD | D3.4.1 | Which external product intefaces with permanent database backend? | Initial external function that interfaces with permanent database backend specifically functions | Y | Y | D5 | S1_PRD_D3.4.1_(AorM)_(time)
S1 | PRD | D3.4.k | Which external product intefaces with permanent database backend? | Kth external function that interfaces with permanent database backend specifically functions | Y | Y | D5 | S1_PRD_D3.4.k_(AorM)_(time)
S1 | PRD | D3.5.1 | Which external product intefaces with in-memory database backend? | Initial external function that interfaces with in-memory database backend specifically functions | Y | Y | D5 | S1_PRD_D3.5.1_(AorM)_(time)
S1 | PRD | D3.5.i | Which external product intefaces with in-memory database backend? | Ith external function that interfaces with in-memory database backend specifically functions | Y | Y | D5 | S1_PRD_D3.5.i_(AorM)_(time)
S1 | PRD | D2.2.1 | For function 1, lets scope its impact? Show tickboxes for all public webapp, private webapp, public BFF, private BFF, permanent database, in-memory database, any external links | Does it impact public webapp, private webapp, public BFF, private BFF, permanent database, in-memory database, any external links? (Enumerate all the infrastructure as captured in section 1.6 and section 3) | Y | Y | D5 | S1_PRD_D2.2.1_(AorM)_(time)
S1 | PRD | D2.2.x | For function x, lets scope its impact? Show tickboxes for all public webapp, private webapp, public BFF, private BFF, permanent database, in-memory database, any external links | Keep on scope checkbox questions for all functions from 1-x as above. | Y | Y | D5 | S1_PRD_D2.2.x_(AorM)_(time)
S1 | PRD | D5 | Autogenerated checks start | Check start | N | N | Statement only | S1_PRD_D5_(AorM)_(time)
S1 | PRD | D5.1.1 | Self-check of function 1. Description and scope not clear. Something missing in description or ambiguious? | Self-check for functions is from D5.1.1->D5.x.x. Self-check involves following: 1) Check summary and work out expected impact on all infrastructure like public webapp, private webapp, public BFF, private BFF, permanent database, in-memory database, any external links using LLM. Compare to manually entered values in D2.2.x. Is this same, if expected not same as entered, raise ambiguity, assumption or open question. 2) Compare the product description( section 1.2) vs D5.x.x to work out if any user impact is missing? any users not recorded or missing? | N | Y | Checks for assumptions, ambiguities and open questions. | S1_PRD_D5.1.1_(AorM)_(time)
S1 | PRD | D5.1.2 | Check function 1 vs function 2. Are they overlapping? | 1) Check function 1 summary vs function 2 summary. Are they similar or different? If similar, raise ambiguity. 2) Can they be combined into one function although dissimilar by design? Raise open question after LLM analysis. If better to be 2 different functions, then dont raise open question. | N | Y | Checks for assumptions, ambiguities and open questions. | S1_PRD_D5.1.2_(AorM)_(time)
S1 | PRD | D5.1.3 | Check function 1 vs function 3. Are they overlapping? |  | N | Y | Checks for assumptions, ambiguities and open questions. | S1_PRD_D5.1.3_(AorM)_(time)
S1 | PRD | D5.1.x | Check function 1 vs function x. Any overlap between description? |  | N | Y | Checks for assumptions, ambiguities and open questions. | S1_PRD_D5.1.x_(AorM)_(time)
S1 | PRD | D5.2.1 | Check function 2 vs function 1. Any overlap or ambiguity or assumption or open |  | N | Y | Checks for assumptions, ambiguities and open questions. | S1_PRD_D5.2.1_(AorM)_(time)
S1 | PRD | D5.2.2 | Self-check of function 2 |  | N | Y | Checks for assumptions, ambiguities and open questions. | S1_PRD_D5.2.2_(AorM)_(time)
S1 | PRD | D5.x.1 | Check function x versus 1. Any overlap between description or any ambiguity? |  | N | Y | Checks for assumptions, ambiguities and open questions. | S1_PRD_D5.x.1_(AorM)_(time)
S1 | PRD | D5.x.x | Self-check of function x. |  | N | Y | Checks for assumptions, ambiguities and open questions. | S1_PRD_D5.x.x_(AorM)_(time)
S2 | PRD | D4 | Context Diagram of Product | LLM to be requested to generate a context diagram of entire product based on all the above content reviewed. | N | Y