## Pipeline
Stage | Stage Name | Type | Precursor | Author (LLM / Manual) | Reviewer | Deliverable 1 | Deliverable 2 | Deliverable 3 | Deliverable 4 | Deliverable 5 | Ollama Models Used | Rework / Feedback Loop | Feasibility | Risk | Notes
1 | Product Requirements Document (PRD) | Manual+LLM | N/A | Manual (primary author) | DeepSeek-R1:7b (content review) Gemma3:4b (structuring) | List of functions / systems | Generic description of each function | External product/system linkages | C4 Context Diagram | Open questions, assumptions, ambiguities | deepseek-r1:7b gamma3:4b | If Stage 3 rejects requirements → return here to expand scope/functions | High | LOW | Gemma3:4b is excellent for structuring. DeepSeek-R1 excels at reasoning over ambiguity.
2 | System Requirements Specification (SRS / FRS) | Manual+LLM | 1 | Manual (D1) LLM generation (D2–D5) | Qwen2.5-Coder:7b (review) Gemma3:4b (structuring) | Detailed requirements: Frontend, Android, BFF, Backend | High-level state machines | Flowcharts of functions | C4 Container Diagram | System invariants document | qwen2.5-coder:7b gamma3:4b | If Stage 3 raises contradictions → return here to resolve specific requirement conflicts | High | MED | State machines and flowcharts are well within Qwen2.5-Coder capability. Validate invariants manually — LLMs miss negative constraints.
3 | Requirements Validation Gate | Gate | 2 | Manual (D1–D4) Qwen2.5-Coder:7b (D5 — final approved doc) | DeepSeek-R1:7b | Contradiction review | Ambiguity review | Missing requirements review | Concurrency & offline-risk review | Approved finalized requirements (PRD / SRS / FRS) | deepseek-r1:7b qwen2.5-coder:7b | GATE: Fail → return to Stage 1 or 2 depending on failure type | High | MED | DeepSeek-R1:7b is the right model here — strongest reasoning. Concurrency/offline review is the hardest; expect manual iteration.
4 | Software Requirements Document (Architecture + Contracts) | LLM+Manual | 3 | Qwen2.5-Coder:7b | Manual review | Data schema of functions | UML diagrams of functions | OpenAPI YAML files | PlantUML screen stencils (Frontend / Android) | C4 Component Diagram | qwen2.5-coder:7b | If Stage 5 finds architecture issues → return here to revise schemas / OpenAPI contracts | High | MED | OpenAPI YAML generation is reliable with Qwen2.5-Coder. PlantUML stencils need manual review for accuracy. Define a strict YAML template to constrain output.
5 | Security & Architecture Validation Gate | Gate | 4 | DeepSeek-R1:7b | Manual review | Security review | Offline sync / race-condition review | Architecture consistency review | Dependency validation review | Architecture freeze approval | deepseek-r1:7b | GATE: Fail → return to Stage 4 to revise contracts/schemas | High | MED | R1:7b handles multi-step security reasoning well. Offline sync edge cases need explicit scenario prompts — don't leave it open-ended.
6 | SDD + Atomic Task Generation | LLM+Manual | 5 | Qwen2.5-Coder:7b (or Qwen3:4b for lighter tasks) | Manual review | Atomic task list (1:1 to implementation) | Deployment / configuration manual | Folder structure & repository layout | Dev & curl-based verification document | Dependency graph JSON + context packets | qwen2.5-coder:7b qwen3:4b | If Stage 8 reveals missing schema/contract → return here to insert missing tasks and update dependency graph | CRITICAL | HIGH | HARDEST STAGE. Context packet schema must be defined before LLM runs. Each packet should carry: task ID, relevant OpenAPI slice, relevant schema fragment, PlantUML screen ref, acceptance test (curl). Token budget per packet: target ≤3k tokens.
7 | Task Validation Gate | Gate | 6 | Manual review | Qwen3:4b | Oversized task detection | Hidden dependency review | Task ambiguity review | Context-window suitability review | Approved task graph | qwen3:4b | GATE: Fail → return to Stage 6 to split tasks / enrich context packets | High | LOW | Define explicit thresholds: max task size = 1 file + 1 function. Context-window suitability: flag any task whose packet + generated code would exceed 6k tokens for Qwen2.5-Coder:7b.
8 | Local Task-by-Task Code Generation | LLM+Manual | 7 | Qwen2.5-Coder:7b (or Llama3:8b for general logic) | Manual + DeepSeek-R1:7b (code review) | Generated code | Unit tests | Updated DTOs / interfaces if needed | Implementation notes | Code review findings | qwen2.5-coder:7b llama3:8b deepseek-r1:7b | DTO/interface change discovered → flag to Stage 6 to update contracts; re-run affected downstream tasks only | High | MED | Run one task at a time. Feed context packet + prior implementation notes into each prompt. DeepSeek-R1 for review is smart — it will catch logic errors Qwen misses.
9 | Integration & Deployment Validation | Mixed | 8 | Phi3:mini / Qwen3:4b (D1) Manual (D2–D5) | Manual review | Integration validation report | Contract mismatch review | Regression verification checklist | Deployment readiness review | Release approval | phi3:mini qwen3:4b | Contract mismatch found → return to Stage 4 (contracts) and cascade through 5→6→7→8 | High | LOW | Phi3:mini is sufficient for diff-based contract validation. Keep a running mismatch log from Stage 8 to feed into this stage automatically.

## Context Packet Schema
Field | Type | Required | Description | Example
task_id | string | Yes | Unique task identifier from dependency graph | TASK-042
task_name | string | Yes | Short human-readable name | Implement POST /users endpoint
depends_on | array | Yes | List of task_ids this task depends on | ["TASK-038", "TASK-039"]
target_file | string | Yes | Exact file path to create/modify | src/routes/users.ts
target_function | string | Yes | Function/class/method name to implement | createUser()
openapi_slice | yaml | Yes | Relevant OpenAPI YAML snippet for this endpoint | /users: post: ...
schema_fragment | json | Yes | Relevant data schema (DTO / DB model) | {"name": "string", "email": "string"}
plantUML_screen_ref | string | No | Reference to PlantUML screen stencil ID if UI task | SCREEN-05-RegisterForm
acceptance_test | string | Yes | curl command or test assertion to verify implementation | curl -X POST /users -d '{...}'
implementation_notes | string | No | Any prior notes from earlier tasks affecting this one | Reuse authMiddleware from TASK-031
token_budget_target | integer | Yes | Max tokens for prompt (packet + generated code) | 3000
llm_prompt_template | string | Yes | Prompt template referencing above fields | Implement {target_function} in {target_file}. Contract: {openapi_slice} ...

## Model Reference
Ollama Model | Pull Command | VRAM (~) | Strengths | Stages Used | Notes
deepseek-r1:7b | ollama pull deepseek-r1:7b | ~6 GB | Multi-step reasoning, contradiction detection, security analysis | 1, 3, 5, 8 | Best model for validation gates. Slow but thorough. Use for review, not generation.
qwen2.5-coder:7b | ollama pull qwen2.5-coder:7b | ~6 GB | Code generation, OpenAPI YAML, schemas, UML, SRS generation | 2, 4, 6, 8 | Primary workhorse for all code-adjacent generation. Strong instruction following.
gemma3:4b | ollama pull gemma3:4b | ~4 GB | Document structuring, formatting, light summarisation | 1, 2 | Use for structuring/formatting only. Not reliable for reasoning or code.
qwen3:4b | ollama pull qwen3:4b | ~4 GB | Task validation, context-window checks, lightweight generation | 6, 7, 9 | Note: verify exact model name on Ollama hub — may be qwen2.5:3b or similar.
llama3:8b | ollama pull llama3:8b | ~6 GB | General logic, non-code reasoning, prose generation | 8 | Alternative to Qwen2.5-Coder for general logic tasks within code gen stage.
phi3:mini | ollama pull phi3:mini | ~2 GB | Lightweight diff/contract validation, integration report gen | 9 | Very fast. Suitable for structured comparison tasks at integration stage.

## Legend
Colour / Symbol | Meaning
Red row (Gate) | Validation gate — pipeline cannot proceed without approval
Amber author column | Manual human authoring required
Blue author column | LLM generates output
Salmon rework column | Rework / feedback loop path if gate fails
Risk: CRITICAL (purple) | Highest risk stage — quality here determines all downstream output
Risk: HIGH (red) | High risk — requires careful manual review
Risk: MED (orange) | Medium risk — LLM output is generally reliable but needs spot-checks
Risk: LOW (green) | Low risk — well-defined task, model performs reliably